| Decarbonisation |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- |
| Our Vision (how can you reduce emissions and support students to be part of the transition to net zero?): To reduce emissions through practical steps in energy use, transport, and resource efficiency—while empowering our pupils to understand and take part in the transition to net zero. |  |  |  |  |  |  |
| Action | Link to Improvement Plan | Responsibility and Key Stakeholders | Timescale | Information and/or resources required | Target/ Measure | Progress (Update at regular review points) |
| Conduct an energy audit of the school buildings | Premises improvement priority | Headteacher, caretaker, Eco-Committee | Start date: Autumn 2025 Review Date: July 2026 | Local authority support or Energy Sparks tool | Complete audit and identify top 3 energy-saving actions |  |
| Replace all lighting with LED bulbs / other low energy emitting blubs | Linked to energy use efficiency | Governors, site manager | By Spring 2026 | Budget approval, electrician | 100% LED lighting/ low energy emitting in all rooms | Blubs replaced in three classrooms. Blubs in hall replaced but not LED as do not exist for fittings. |
| Promote walk-to-school initiatives | Linked to health and wellbeing priorities | Headteacher, Ethos Group, parents | Ongoing | Travel plan resources, Sustrans materials | 10% reduction in car drop-offs | Difficult to promote in rural area however, will try and promote those in the village |
| Useful Links: https://energysparks.uk https://www.sustrans.org.uk |  |  |  |  |  |  |

Sustainability and Climate Action Plan – Lythe Primary School

| Adaptation and Resilience |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- |
| Our Vision (how can you adapt your buildings and systems to prepare for the effects of climate change?): To adapt our buildings and systems to better cope with extreme weather, while teaching children to understand local climate risks and build resilience. |  |  |  |  |  |  |
| Action | Link to Improvement Plan | Responsibility and Key Stakeholders | Timescale | Information and/or resources required | Target/ Measure | Progress (Update at regular review points) |
| Install water butts to collect rainwater | Linked to outdoor learning | Eco-Committee, PTA | Spring 2026 | Water butts, staff volunteer to install | Reduce use of mains water for garden by 80% |  |
| Review drainage and flood resilience around the site | Site safety priority | Site manager, governors | Autumn 2025 | Liaise with local council | Action plan completed |  |
| Create shaded outdoor spaces for summer learning | Health/wellbeing strategy | Forest School lead, SLT | Summer 2026 | Budget/funding, parent help | Create 2 shaded outdoor zones | Peace garden already shaded and used. Another area (on the field in the shade) to be created. |
| Useful Links: https://www.rhs.org.uk/advice/profile?pid=988 |  |  |  |  |  |  |

| Biodiversity |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- |
| Our Vision (how can you enhance biodiversity, improve air quality and increase access to, and connection with, nature?): To enhance biodiversity across the school grounds, support local wildlife, and connect children to the natural world through hands-on experiences. |  |  |  |  |  |  |
| Action | Link to Improvement Plan | Responsibility and Key Stakeholders | Timescale | Information and/or resources required | Target/ Measure | Progress (Update at regular review points) |
| Create a wildflower meadow or pollinator patch | Outdoor learning/Science link | Eco-Committee, gardening club | Spring 2026 | Seeds, tools, staff volunteers | 15m² planted for pollinators |  |
| Install bird boxes and bug hotels | Linked to science curriculum | Forest School lead, pupils | Autumn 2025 | Local wildlife trust guidance | 5 habitats created on site | 3 bird boxes so far located around the school. Bug hotel to be built at new allotment. |
| Arrange take over of alloment from Mulgrave Estate to grow our own produce. | Linked to outdoor learning | Governor, Head and Class teachers | Summer 2026 | Agreement with estate, meet with former owner to discuss handover. | Sustainable allotment to grow own produce | Take over happens on 1st December. Work to be done on a new shed to store equipment. |
| Hold a “No Mow May” zone | Biodiversity enhancement priority | Caretaker, school council | May each year | Signage, community support | 1 zone left uncut each May |  |
| Useful links: https://www.wildlifetrusts.org https://plantlife.love-wildflowers.org.uk |  |  |  |  |  |  |

| Climate Education and Green Skills |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- |
| Our Vision (how can you prepare students for a world impacted by climate change through education & practice?): To ensure every child leaves Lythe Primary with the knowledge, values, and skills to contribute to a sustainable future. |  |  |  |  |  |  |
| Action | Link to Improvement Plan | Responsibility and Key Stakeholders | Timescale | Information and/or resources required | Target/ Measure | Progress (Update at regular review points) |
| Integrate sustainability themes into science, geography, and PSHE | Curriculum enrichment priority | Subject leads, SLT | Ongoing from Autumn 2025 | Curriculum review, Eco-Schools framework | At least one topic per term with climate focus |  |
| Join the Eco-Schools programme | Pupil leadership and curriculum | Eco-Coordinator, school council | Register Autumn 2025 | https://www.eco-schools.org.uk | Earn Bronze award by Summer 2026 | Signed up to join eco-schools November 2025. |
| Run a pupil-led sustainability week and invite guest speakers and visits – Beacon Farm (Bees and self-sustain), Fair Trade (local supermarkets) and Wendy Welford (solar panels). | Linked to pupil engagement | Teachers, PTA, local community | Summer 2026 | Speakers, workshops, activity ideas | 100% pupil participation |  |
| Useful Links: https://www.eco-schools.org.uk https://transform-our-world.org |  |  |  |  |  |  |